## Slide 1: BHCG and Centivo: Communication and Change Management Toolkit Template
August 2021

## Slide 2: About This Document
The purpose of this document is to provide recommended communication and change management actions and resources you can leverage to launch Centivo, either as your medical plan option or alongside another option. Here’s what is included in the following pages:
Pages 3 - 5 Change Management Guidance
Pages 6 - 7 Goals and Audiences
Pages 8 - 10 Communication Plan
Pages 11 - 12 Key Messages, FAQs and Challenges
Pages 14 - 20 Centivo Communication Support

## Slide 3: Guiding Principles for Change
Ensure the people, process and tools are in place for lasting change
Provide the tools and support needed to build the future
Involve people to identify needs, take action, and mitigate risks
Envision
Engage
Embed
Enable
Bring the change to life for people and define how it impacts them
4Es
Keep these 4Es in mind as you plan for and roll out the change

## Slide 4: What Successful Change Looks Like
Story
A clearly articulated and compelling story
Alignment
Aligned people, programs, processes, technology
Leadership
Leaders who actively support and advocate change
Capability
Organizational capability
to change
Sustainability
Lasting change
and resiliency
Keep these success characteristics in mind as you plan your efforts

## Slide 5: Tips for Managing Change Well
  Start Early
1
2
3
4
5
  Get Agreement on Key Messages
  Test Approach with Employees
  Consider What Else is Going On
  Insist Leaders Be Visibly Involved
  Create Foundational Communications
6
7
8
9
10
  Put Employees at the Center of the Story
  Position the Decision as Final
  Lead with the Honest “Why”
  Go High Tech and High Touch
Bonus
  Remember Employees Are More Resilient Than We Think
Consider these tips based on experience with hundreds of employers

## Slide 6: Communication and Change Goals
Message Clearly
  Consistently convey key messages from the employer voice that demonstrate the value of the Centivo model to all audiences
Encourage Participation
  Encourage employees to consider, select and take full advantage of Centivo
Transition Well
  Create transition communications based on the Centivo option you’re incorporating*
Build Knowledge
  Use this opportunity to increase employee medical benefits IQ
Increase Trust
  Increase understanding of why members should value the PCP relationship and increase comfort with and trust of their PCPs over time
Aim toward these goals for a successful rollout and ongoing change management
*Employer responsibility

## Slide 7: Audiences to Reach
Reach each of these audience groups with your key messages
Members | Leaders | External
Employees* Retirees (pre- and post-65) Spouses/Partners Call Center Staff (who talk with members) Quantum | CEOs Leaders HRBPs Managers | Network Health Providers Media/Press Vendor Partners Advisors
*All benefit eligible, those offered Centivo as only option, those offered Centivo as the only option, those newly eligible (e.g., new hires, turning age 26), members outside of a Centivo network area, HPS

## Slide 8: Plan Framework by Phase
Members
Leaders
External
Phases | Prepare | Engage/Activate | Support
Goals |  |  | 
Themes |  |  | 
Roll out your communications in phases based on when you are offering Centivo
Better experience with trusted, proven PCPs & high-quality providers
Stories of satisfied members
Cost and quality results in Eastern WI
Cost and quality results in our company
Savvy business decision, sustainable cost management
Support, encouragement, and role modeling for employees
Smart community decision
Takes waste and mystery out of the system
Give audiences time to adjust and learn
Reflect the ease of the plan in the enrollment approach
Guide individual members to maximize experience
Lower cost sharing (lower premiums, less out of pocket), better care support more successful company, impact greater good

## Slide 9: Plan At-A-Glance: Members
 = Centivo Can Create, Employer Involved in Tailoring
Members
Leaders
External
Feedback
Prepare (~6 weeks before OE) | Engage/Activate (during OE) | Equip (after OE)
“You’re Enrolled” Communication  | Centivo comm after enrollment
“Activate” Communication  | Centivo comm before plan year
“See PCP & Get Referrals” Communication  | Centivo comm after activation
“Make a Change” Communication  | Centivo comm when course correction needed
“Change Your Enrollment” Communication  | Centivo comm when there’s a life event
Slides, Meetings, Webinars  | Webinar just on Centivo offer, times for families
Health Care 101 Campaign | Brief videos & other comms to increase literacy
Meet Centivo Video  | Promotional video highlighting key features
FAQs  | Answers to anticipated questions
Transition Communication | Showing what’s changing, comparing differences
Oversized Postcard to Homes | Leverage Centivo content to mail home
NOTES: Centivo allows employees to chose their preferred communication channels for the system-generated communications; retirees may receive their communications by mail.
Testimonials  | Stories shared in various channels
Testimonials  | Stories shared in various channels
OE Handouts With Analogies | Overview of Centivo and how it works
Searchable Provider Directory  | Publicly-available website with directory of network providers on Centivo site with clearly-labeled network lists (link will be embedded in various communications)
Benefit Fair Giveaways  | Giveaways for in-person events
Welcome Communications | Activation kit and ID for enrollees
Announcement | Introducing Centivo as a new benefit
Testimonials  | Stories shared in various channels
Members
Live Meetings – like benefit fairs | Centivo live, other vendors online
Quantum Training | Training Quantum on medical records transfer
Call Center Training | Training call center staff on the Centivo details

## Slide 10: Plan At-A-Glance: Other Audiences
 = Centivo Can Create, Employer Involved in Tailoring
Members
Leaders
External
Feedback
Prepare | Engage/Activate | Equip
Pulse Survey and/or Focus Groups (All) | Gathering input from key audiences
Educational Guide (Providers)  | Centivo education for providers
FAQs (All) | Answers to expected questions
Announcement (Vendors, Advisors) | Overview for those working with company
Announcement (All) | Heads up on Centivo before employees
Talking Points about Prepare (All) | Key points to convey in this phase
Talking Points about Enroll (All) | Key points to convey in this phase
Talking Points about Equip (All) | Key points to convey in this phase
Press Release (Media) | Announcing Centivo offering for employer
Educational Guide (Providers)  | Centivo education for providers
Training Presentation (HR, Managers) | Equipping HR and managers
Member List (Providers)  | List of members who’ve designed them as PCP
Template Letters/Emails (Providers)  | For welcoming members to their practice
Business Presentation (CEO, Leaders) | Overview of offer and communication approach
Business Presentation (CEO, Leaders) | Overview of offer and communication approach
Leaders
External
Feedback
Pulse Survey and/or Focus Groups (All) | Gathering input from key audiences
Press Release (Media) | Update on progress & results as appropriate
US Health Care Cost Map | Infographic illustrating higher relative WI costs

## Slide 11: Consistent Key Messages and FAQs
See separate documents for key messages and FAQs
Use the key messages and FAQs in the Word document so you consistently convey the main messages to your various audiences and stay consistent with other WI employers

## Slide 12: Addressing the Toughest Challenges
Some Top Challenges | Solution Built into Plan
Most employees have a low level of medical benefits literacy—starting with not knowing what a PCP is or does | Weave in relevant testimonials, analogies and examples they can relate to and that illustrate the Centivo advantages; get to the lowest common denominator of knowledge and define what we’re talking about along the way; highlight key messages and point people to specific details if they want more
As many as 25% of the population will need to change PCPs | Be prepared with messages about the quality of the in-network PCPs and the advantages of the way they are there to help you navigate with the Centivo model; coach members through making the transition in practical ways and emphasize that the model saves time and reduces the hassle of finding specialists
This model differs from the UHC Premium Designation model that we said was very important | Focus on the advantages of the Centivo model versus what’s not good about any other model; emphasize that the current approach is not working and we’re always looking for better ways to deliver health care more affordably
It’s hard to reach spouses/partners | Consider a home mailing and webinars
The PCP “gatekeeper” approach seems like de ja vu…seems like we’re back to the old HMO world | Emphasize that the Centivo model is designed to provide you the right guided care at the right time; it’s not trying to prevent you from receiving care; rather, the focus is on getting you quality care when you need it without wasting your time or money
Address the potential challenges and questions by building in solutions in advance

## Slide 13: Centivo Communication Support
Work with the Centivo team to leverage the wide range of materials they can work with you to customize and co-brand; the content is available to you in a designed format or in Word
Privileged and Confidential
Centivo Learnings
Require active enrollment for all employees
Host dedicated webinars/meetings about the new offerings
Invite health system representatives to the employee meetings/webinars
Be transparent about why you made the change, and don’t be afraid to “sell” the new plans
Communicate early and often
Showcase total expected costs and how the new option will save them money
Provide separate/standalone materials and communications about the new benefits (with help from Centivo), including a brochure or 1-pager, provider directory, etc.

## Slide 14: Appendix: Centivo Template Communications

## Slide 15: Employee Members: Centivo Communication Support
Benefit fair giveaways
OE hand-outs
Slides, meetings & webinars
We make change management easy through open enrollment communication and support
Materials:
Customized to your key messages
Co-branded
On-site / virtual support:
(Virtual) benefit fair staffing
OE meetings & webinar support
Hands-on activation support
Searchable provider directory
Privileged and Confidential

## Slide 16: Welcome Communications: Partnership Plan
Envelope
Inside folder
Brochure
ID card mailer
Magnet
Spanish Insert
Privileged and Confidential

## Slide 17: Welcome Communications: Traditional Plans
ID card mailer
Inserts w/ key plan details
Privileged and Confidential

## Slide 18: Employee Materials: Centivo ID Card
Privileged and Confidential
ID Card – Partnership Plan
ID Card – Traditional Plans
Digital ID Card

## Slide 19: Provider Communication
We send providers:
A list of members who have designated them as their PCP
Template letters/emails that they can send to members to welcome them to their practice
Privileged and Confidential

## Slide 20: Employee Members: Centivo Plan Experience
Ongoing, year-round communication to help people get the most out of the plan.
Help them do what they need to do when they need to do it:
“You’re enrolled”
After enrollment
“Activate”
Before plan year
“See your PCP and get referrals”
After activation
“Next time do it differently for lower costs”
When they need a course correction
“Change your enrollment”
When life circumstances change
Members choose how they want to hear from us.
Options include: Email, In-app or portal, text message, app push notification, and physical mail.
Privileged and Confidential